## exact name of registrant a
(Exact name of registrant as specified in its charter)
Nevada | 000-50028 | 46-0484987
(State or other jurisdiction of incorporation) | (Commission File Number) | (I.R.S. Employer Identification No.)
WYNN LAS VEGAS, LLC
(Exact name of registrant as specified in its charter)
Nevada | 333-100768 | 88-0494875
(State or other jurisdiction of incorporation) | (Commission File Number) | (I.R.S. Employer Identification No.)

## table of contents
TABLE OF CONTENTS
PAGE
ARTICLE 1. DEFINITIONS; RULES OF INTERPRETATION |  | 1
1.1 | Definitions | 1
1.2 | Rules of Interpretation | 1
ARTICLE 2. ACCOUNTS AND PROJECT DATE PROCEDURES |  | 2
2.1 | Company Accounts | 2
2.2 | [RESERVED] | 2
2.3 | [RESERVED] | 2
2.4 | [RESERVED] | 2
2.5 | [RESERVED] | 2
2.6 | [RESERVED] | 2
2.7 | Completion Date Procedures | 2
2.8 | Completion Guaranty Release Procedures | 3
2.9 | Final Completion Procedures | 4
ARTICLE 3. [RESERVED] |  | 4
ARTICLE 4. REPRESENTATIONS AND WARRANTIES |  | 4
4.1 | Permits | 5
4.2 | In Balance Requirement; Schedule | 5
4.3 | Sufficiency of Interests and Project Documents | 5
4.4 | Project Budget; Summary Anticipated Cost Report | 6
4.5 | Project Schedule | 7
4.6 | Plans and Specifications | 7
ARTICLE 5. AFFIRMATIVE COVENANTS |  | 8
5.1 | Excess Cash Flow | 8
5.2 | Diligent Construction of the Phase II Project | 8
5.3 | [RESERVED] | 9
5.4 | Reports; Cooperation | 9
5.5 | Certain Transfers from Completion Guaranty Deposit Account. | 10
5.6 | Notices | 10
5.7 | Construction Consultant | 11
5.8 | As-Built Survey | 12
5.9 | Payment and Performance Bonds | 12
5.1 | [RESERVED] | 12
5.11 | [RESERVED] | 12
5.12 | [RESERVED] | 12
5.13 | Insurance | 12
5.14 | Application of Insurance and Condemnation Proceeds | 12

## table of contents-1
ARTICLE 6. NEGATIVE COVENANTS |  | 13
6.1 | Waiver, Modification, Termination and Amendment of Permits and Contracts | 13
6.2 | Scope Changes | 13
6.3 | Project Budget and Project Schedule Amendment | 13
6.4 | Additional Construction Agreements | 15
6.5 | Liens Releases | 15
6.6 | Title Policy Endorsement | 15
6.7 | Construction Progress | 16
6.8 | Contracts for Phase II Project | 16
ARTICLE 7. EVENTS OF DEFAULT |  | 17
7.1 | Events of Default | 17
7.2 | Remedies | 19
ARTICLE 8. CONSULTANTS AND REPORTS |  | 20
8.1 | Removal and Fees | 20
8.2 | Duties | 20
8.3 | Acts of Disbursement Agent | 20
ARTICLE 9. THE DISBURSEMENT AGENT |  | 20
9.1 | Appointment and Acceptance | 20
9.2 | Duties and Liabilities of the Disbursement Agent Generally | 21
9.3 | Particular Duties and Liabilities of the Disbursement Agent | 22
9.4 | Segregation of Funds and Property Interest | 24
9.5 | Compensation and Reimbursement of the Disbursement Agent | 24
9.6 | Qualification of the Disbursement Agent | 24
9.7 | Resignation and Removal of the Disbursement Agent | 25
9.8 | Merger or Consolidation of the Disbursement Agent | 25
9.9 | Statements; Information | 25
9.1 | Limitation of Liability | 25
ARTICLE 10. SAFEKEEPING OF ACCOUNTS |  | 26
10.1 | Application of Funds in Company Accounts | 26
10.2 | Event of Default | 26
10.3 | Liens | 27
10.4 | Perfection | 27
ARTICLE 11. MISCELLANEOUS |  | 27
11.1 | Addresses | 27
11.2 | Delay and Waiver | 28
11.3 | Entire Agreement | 28

## table of contents-2
11.4 | Governing Law | 29
11.5 | Severability | 29
11.6 | Headings | 29
11.7 | Limitation on Liability | 29
11.8 | Waiver of Jury Trial | 29
11.9 | Consent to Jurisdiction | 29
11.1 | Successors and Assigns | 30
11.11 | Reinstatement | 30
11.12 | No Partnership; Etc. | 30
11.13 | Costs and Expenses | 30
11.14 | Counterparts | 31
11.15 | Termination | 31
11.16 | Binding Effect; Amendment and Restatement | 31
11.17 | Amendments | 32

## addresses
Addresses
If to the Company: | Wynn Las Vegas, LLC
3131 Las Vegas Boulevard South
Las Vegas, Nevada 89109
Attn: Ronald J. Kramer
Telephone No.: (702) 770-7000
Facsimile No.: (702) 770-1100
With a copy to: | Wynn Resorts, Limited
3131 Las Vegas Boulevard South
Las Vegas, Nevada 89109
Attn: General Counsel
Telephone No.: (702) 770-2112
Facsimile No.: (702) 770-1349
If to the Bank Agent: | Deutsche Bank Trust Company Americas
c/o Deutsche Bank Securities Inc.
200 Crescent Court, Suite 550
Dallas, TX 75201
Attn: Gerard Dupont
Telephone No.: (214) 740-7913
Facsimile No.: (214) 740-7910
If to the Disbursement Agent: | Deutsche Bank Trust Company Americas
60 Wall Street, 11th Floor
New York, New York 10005
Attn: Amy Sinensky
Telephone No.: (212) 250-4063
Facsimile No.: (212) 797-4885